****

**Africa Trade Union Development Network (ATUDN)**

**Annual Plan May 2016-May 2017**

| **Intervention Area** | **Key Trade union actors** | **Target organisations** | **Expected results** | **Activities** | **Implementation strategy & working tools** | **Time frame** |
| --- | --- | --- | --- | --- | --- | --- |
| 1. **Advocacy**
 |
| 1.1. Baseline Assessment Survey on: Trade Union SDGs monitoring strategies at the regional and national level | ITUC-AfricaTU Sub-regional organisationsSelected national centres | National governments | -A report on African TU SDGs monitoring strategies at the national and regional levels | A baseline assessment A pilot assessment of 5 countries across the region.  | The activity shall be coordinated by ITUC-Africa through the ATUDN. The sub-regional TU organizations (SATUCC, EATUCC & OTUWA) shall be responsible for the collection of sub-regional information and the ATUDN members shall be responsible for collection of information at the national level.An interview guide/questionnaire shall be developed | June-September 2016 |
| 1.2. Mapping on* Agenda 2063
* Agenda 2030

With Sub-regional economic blocks, governments as well as progressive CSOs at the national level | -ITUC-Africa-EATUCC, SATUCC & OTUWA-National centres | -African Union Commission-The AU Trade & Industry Commission & Economic Affairs -UN Economic Commission for Africa (UNECA)-Sub-regional economic organisations (ECOWAS, SADC, EAC, Maghreb region)-Progressive CSOs at the national, regional levels | -Established links with the identified organisations  | Development of a database on all planned activities relating to Agenda 2030 as well as the AU 2063 at the national, sub-regional and regional levels.  | The activity shall be coordinated by ITUC-Africa through the ATUDN. ITUC-Africa shall communicate with the regional organisations (AU). The sub-regional organisations shall be tasked with making contacts with sub-regional organisations and provide feedback to ITUC-AfricaThe national representative members of the network shall be expected to link up with relevant government Agencies responsible for development and economic issues in their countries. | June 2016 |
| 1.3 Setting of TU priorities at national level | -ITUC-Africa-EATUCC, SATUCC & OTUWA-National centres | National unions | National trade union priorities on SDG implementation and monitoring established  | Discussions in the Regional Meeting to identify national priorities | ITUC-Africa in coordination with sub-regional organisations | September 2016 |
| 1.4 Implementation and monitoring of the SDGs | -ITUC-Africa-EATUCC, SATUCC & OTUWA-National centres | Regional and sub-regional institutions, national governments | -TU watch” on A2030 implementation-A permanent shadow report at national level on A2030 implementation |  Research and advocacy. | ITUC-Africa in coordination with sub-regional and national organisations | Shadow report by end of 2017 |
| 1.5. ACTRAV SDGs workers academy | ITUC-Africa, sub-regional organisations and national centres |  |  |  |  | 9-20 May 2016 |
| 1.6. Deepening the research on PPPs and social dialogue | ITUC-AfricaSub-regional organisationsA selected national centres | National governmentsDevelopment cooperation partnersPrivate sectorWorkers on PPPs projects | An updated/advanced report on the nature and impact of PPPs on development and generally working conditions in Africa Country case studies on the relevance of social dialogue for developmentA trade union strategy for engagement on PPPsStrategies for engagement in social dialogue | Research & policy analysis | Coordination by ALREI and ATUDN | July-August 2016 (PPPS)Timeline for social dialogue (tbc) |
| 1. **Partnerships/ Organisational capacity**
 |
| 2.1. TU Solidarity partnerships meeting & introduction of TUDEP | ITUC-AfricaITUC | Trade union centres engaged in development partnershipsSub-regional trade union organisationsNational trade unions centres | Better identification of synergies between the work of various SSOs and affiliates | Meeting and training workshop | Coordinated by TUDCN in collaboration with ATUDN | March 2016 |
| 2.2. Baseline study on TU organizational capacity  | ITUC-Africa | Sub-regional TU organisationsNational CentresProgressive CSOs at the national level | -Better understanding of the state of trade union organisations in Africa. -An ITUC-Africa well informed and coherent TU program of action towards building and strengthening the capacities of its affiliates. | Baseline survey across a number of TU organisations as at the national level as well as at the sub-regional level | Coordinated by the Africa Labour Research and Education Institute (ALREI). Data collection to be done by national centre organisations | April |
| 1. **Network meetings**
 |
| 2. 3. TUDCN General Meeting | Members of the ATUDN  |  |  |  |  | 5-8 April, Bangkok 2016 |
|  |  |  |  |  |  |  |
| 2.5. ATUDN General meeting | Members of the ATUDN and a selected TU leaders from selected TU centres | General Membership of ATUDN | Strategic perspectives of the ATUDN 2016-2019 ProgramATUDN SDGs engagement strategy | Annual General MeetingPresentations and group activities | Coordinated by the ATUDN | September 2016Venue: Possibility Tunisia or Nairobi (to be confirmed) |
| **3. Visibility & communication** |  |
| 4.1. Group & steering committee mailing lists |  |  |  |  |  | May 2016 |
| 4.2. Webpage |  |  |  |  |  | June 2016 |
| 4.3. Newsletter |  |  |  |  |  | November 2016 |