****

**Africa Trade Union Development Network (ATUDN)**

**Annual Plan May 2016-May 2017**

| **Intervention Area** | **Key Trade union actors** | **Target organisations** | **Expected results** | **Activities** | **Implementation strategy & working tools** | **Time frame** |
| --- | --- | --- | --- | --- | --- | --- |
| 1. **Advocacy** | | | | | | |
| 1.1. Baseline Assessment Survey on: Trade Union SDGs monitoring strategies at the regional and national level | ITUC-Africa  TU Sub-regional organisations  Selected national centres | National governments | -A report on African TU SDGs monitoring strategies at the national and regional levels | A baseline assessment  A pilot assessment of 5 countries across the region. | The activity shall be coordinated by ITUC-Africa through the ATUDN. The sub-regional TU organizations (SATUCC, EATUCC & OTUWA) shall be responsible for the collection of sub-regional information and the ATUDN members shall be responsible for collection of information at the national level.  An interview guide/questionnaire shall be developed | June-September 2016 |
| 1.2. Mapping on   * Agenda 2063 * Agenda 2030   With Sub-regional economic blocks, governments as well as progressive CSOs at the national level | -ITUC-Africa  -EATUCC, SATUCC & OTUWA  -National centres | -African Union Commission  -The AU Trade & Industry Commission & Economic Affairs  -UN Economic Commission for Africa (UNECA)  -Sub-regional economic organisations (ECOWAS, SADC, EAC, Maghreb region)  -Progressive CSOs at the national, regional levels | -Established links with the identified organisations | Development of a database on all planned activities relating to Agenda 2030 as well as the AU 2063 at the national, sub-regional and regional levels. | The activity shall be coordinated by ITUC-Africa through the ATUDN. ITUC-Africa shall communicate with the regional organisations (AU). The sub-regional organisations shall be tasked with making contacts with sub-regional organisations and provide feedback to ITUC-Africa  The national representative members of the network shall be expected to link up with relevant government Agencies responsible for development and economic issues in their countries. | June 2016 |
| 1.3 Setting of TU priorities at national level | -ITUC-Africa  -EATUCC, SATUCC & OTUWA  -National centres | National unions | National trade union priorities on SDG implementation and monitoring established | Discussions in the Regional Meeting to identify national priorities | ITUC-Africa in coordination with sub-regional organisations | September 2016 |
| 1.4 Implementation and monitoring of the SDGs | -ITUC-Africa  -EATUCC, SATUCC & OTUWA  -National centres | Regional and sub-regional institutions, national governments | -TU watch” on A2030 implementation  -A permanent shadow report at national level on A2030 implementation | Research and advocacy. | ITUC-Africa in coordination with sub-regional and national organisations | Shadow report by end of 2017 |
| 1.5. ACTRAV SDGs workers academy | ITUC-Africa, sub-regional organisations and national centres |  |  |  |  | 9-20 May 2016 |
| 1.6. Deepening the research on PPPs and social dialogue | ITUC-Africa  Sub-regional organisations  A selected national centres | National governments  Development cooperation partners  Private sector  Workers on PPPs projects | An updated/advanced report on the nature and impact of PPPs on development and generally working conditions in Africa  Country case studies on the relevance of social dialogue for development  A trade union strategy for engagement on PPPs  Strategies for engagement in social dialogue | Research & policy analysis | Coordination by ALREI and ATUDN | July-August 2016 (PPPS)  Timeline for social dialogue (tbc) |
| 1. **Partnerships/ Organisational capacity** | | | | | | |
| 2.1. TU Solidarity partnerships meeting & introduction of TUDEP | ITUC-Africa  ITUC | Trade union centres engaged in development partnerships  Sub-regional trade union organisations  National trade unions centres | Better identification of synergies between the work of various SSOs and affiliates | Meeting and training workshop | Coordinated by TUDCN in collaboration with ATUDN | March 2016 |
| 2.2. Baseline study on TU organizational capacity | ITUC-Africa | Sub-regional TU organisations  National Centres  Progressive CSOs at the national level | -Better understanding of the state of trade union organisations in Africa.  -An ITUC-Africa well informed and coherent TU program of action towards building and strengthening the capacities of its affiliates. | Baseline survey across a number of TU organisations as at the national level as well as at the sub-regional level | Coordinated by the Africa Labour Research and Education Institute (ALREI). Data collection to be done by national centre organisations | April |
| 1. **Network meetings** | | | | | | |
| 2. 3. TUDCN General Meeting | Members of the ATUDN |  |  |  |  | 5-8 April, Bangkok 2016 |
|  |  |  |  |  |  |  |
| 2.5. ATUDN General meeting | Members of the ATUDN and a selected TU leaders from selected TU centres | General Membership of ATUDN | Strategic perspectives of the ATUDN 2016-2019 Program  ATUDN SDGs engagement strategy | Annual General Meeting  Presentations and group activities | Coordinated by the ATUDN | September 2016  Venue: Possibility Tunisia or Nairobi (to be confirmed) |
| **3. Visibility & communication** | | | | | |  |
| 4.1. Group & steering committee mailing lists |  |  |  |  |  | May 2016 |
| 4.2. Webpage |  |  |  |  |  | June 2016 |
| 4.3. Newsletter |  |  |  |  |  | November 2016 |