|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **TUDCN ACTION PLAN 2014-2015** |  |  |  |
|  | **2014 (second half)** | **DATES** | **interlinkages** | **Explanations** |
| Global Level | 1 Facilitation and Steering Group  | 29-Sep | back to back with the EU Policy Forum on Development (annual meeting) | see proposals to revise composition of FSG |
|   | 1 seminar: TUSSOs and Regions on cooperation modalities  | September | back to back with the FSG | Serious of concerns were raised by different partners when responding to the latest EU call on the informal economy, clearly reflecting the challenge of sharing ownership of trade union projects in the south supported by back-donor budgets. This triggers a broader debate on division of tasks/responsibilities/inputs and sharing resources .This seminar will adress these matters with all parties concerned (regional secretaries, directors of SSO, international cooperation department directors).  |
|   | 1 seminar: trade union meeting with DAC on global agendas  | November |   | Discussions with the DAC secreteriat have been initiated to organise a seminar with trade unions. Focus areas could be on: decent work on the one hand and to take up the issue of ODA definition and the current debate on FfD |
|   | 1 development paper: Guide on M&E  | done |   | This guide has been elaborated thanks to the work of the TUDCN wg on TU development effectiveness. It will serve to support training activites in the South to strenghten capacity in monitoring & evaluation of development programmes |
|   | 1 development paper: social dialogue in development  | November |   | This document is aimed at providing concreate examples on the role of social dialogue in development. It will be based on concreate TU programmes, highlighting their positive results in terms of policy contribution and capacity building of southern actors. This could be used by TUDCN members both for advocacy and fund raising purposes  |
|   | 1 study on HRBA and Private sector (CPDE) | end of the year |   | This CSO Research study on Private Sector in Development and HRBA is supported by the CPDE. It is part of the work plan of the WG on HRBA of the CPDE , which the ITUC is leading. This study will be aimed at gathering evidence on PS results/impact in development from an HRBA perspective.  |
| Regional Level | **ADVOCACY** | **DATES** | **interlinkages** | **Explanations** |
|   | 1 meeting Latin America (CPDE) | tbc |   | This regional meeting is supported by the CPDE. It can be focused on specific policy areas to be agreed with the regions |
|   | 1 meeting Africa (CPDE) | tbc |   | This regional meeting is supported by the CPDE. It can be focused on specific policy areas to be agreed with the regions |
|   | **PARTNERSHIPS** | **DATES** | **interlinkages** | **Explanations** |
|   | 1 meeting AP  | December |   | The aim of this regional meeting will be to discuss the future work on development issues in the region both in terms of advocacy and partnerships together with ITUC-AP and its members.  |
|   | 1 TUSSOs-Latin America  | August | in conjunction with TUSSOs regional meetings | The aim of this regional workshop (back to back with TUSSOs coordination meeting) is to support shared implementation of the TUDEP, gathering evaluation elements, and planning further training activites at regional level on monitoring & eveluation methodologies |
|   | 1 TUSSOs-Africa |  November | in conjunction with TUSSOs regional meetings | The aim of this regional workshop (back to back with TUSSOs coordination meeting) is to support shared implementation of the TUDEP, gathering evaluation elements, and planning further training activites at regional level on monitoring & eveluation methodologies |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  |  |  |  |  |
|  | **2015 (first half)** | **DATES** | **interlinkages** | **Explanations** |
| Global Level | 1 GM Lomé  | March |   |   |
|   | 1 Facilitation and Steering Group  |   | back to back with the EU Policy Forum on Development (annual meeting) | see proposals to revise composition of FSG |
|   | 1 thematic seminar: global governance |   |   | This will be a policy workshop aimed at discussing "global development governance". It will include analysis on current avenues on how to strenghten global accountability and it will be aimed at taking a TU political stand for shared advocacy  |
|   | 1 thematic seminar: OCA (organisational capacity assessment) frameworks |   |   | During the elaboration of the M&E guide some specific aspects emerged related to TUs existing modalities. Especially in the field of organisational capacity assessment (OCA), it was registered that TUs are currently using different methodologies and instruments. OCA criteria, as well as, baselines gathering methodologies are fundamental to build up a coherent approach in supporting organisations in the South, and also a useful tool to strengthen development processes’ ownership. This seminar will be aimed at mapping and analysing OCA frameworks used within TUs partners. This will ultimately serve at launching a shared TUs framework on OCA, with policy guidelines. |
| Regional Level | **ADVOCACY** | **DATES** | **interlinkages** | **Explanations** |
|   | 1 regional seminar |   |   | This regional meeting is supported by the CPDE. It can be focused on specific policy areas to be agreed with the regions |
|   | 1 regional seminar |   |   | This regional meeting is supported by the CPDE. It can be focused on specific policy areas to be agreed with the regions |
|   | **PARTNERSHIPS** | **DATES** | **interlinkages** | **Explanations** |
|   |   |   |   |   |
|   |   |   |   |   |
|   |   |   |   |   |
|   |   |   |   |   |