## Slide 1: TUDCN 2011-12 external evaluation
Evaluation Findings, Conclusions & Recommendations
Presented at the GM in Slangerup (Denmark)
April 17th, 2013

## Slide 2: Contents
Evaluation characteristics
  Evaluation aims, background & scope
  Evaluation approach & methodology
Findings: TUDCN key achievements (2011-2012)
  Network development
  Internal achievements
  External achievements
Conclusions & lessons learned
Recommendations

## Slide 3: I. Evaluation Characteristics

## Slide 4: Evaluation object & scope
Object of the evaluation:
  TUDCN 2011-2012 project, funded by the EU
    Where necessary: taking into account evolutions of the network since 2006
  With special attention to the functioning of the network as the chosen working modality for the TU Development Cooperation

## Slide 5: Evaluation aims
To demonstrate to which extent the TUDCN has been able to produce a specific added value and has the potential to continue doing so in the future;
To account for the use of the resources towards the TUDCN member organisations, the ITUC, donors and the public at large;
To learn lessons from the TUDCN activities, approach and results achieved
  => improvement of the future performance of the network (in particular in relation to the next project that will start in April 2013).

## Slide 6: Evaluation methodology (1)
Inception phase (November – December):
  Initial contacts and discussions with the TUDCN secretariat
  Participation (as observer) in the General Meeting in Paris (November 2012)
Implementation phase (January – March):
  Documentary analysis
  Electronic survey, sent to 245 members
  Interviews with internal and external stakeholders
  Presentation of intermediary findings to the FSG (January 2013)
Synthesis phase (March – April)
  Analysis and triangulation of findings
  Evaluation report
    Draft version => sent to the FSG (March 25)
    Presentation at the GM
    Final evaluation report

## Slide 7: Evaluation methodology (2)
Measures to ensure evaluation utilization:
  Executive summary in English, French, Spanish
  Publication as ‘Development Paper’ on TUDCN’s website
Methodological challenges:
  Nature of TUCDN as a worldwide network
  Poor response rate to the survey (8.6%) => the results obtained might not be representative for the network

## Slide 8
II. Findings: TUDCN key achievements (2011-2012)

## Slide 9: Three related categories of achievements
Internal achievements
External achievements
Network development

## Slide 10: Network development (1/5)
  Broad consensus on the relevance and importance of the network goals
  Goals widely known and understood by members (at least by those moderately to strongly involved in the network)
  Correspond with the members’ expectations towards the network
  Challenge: how to deal with the complexity of members’ interests and expectations when the network becomes more diverse
Good level of trust: (a) in the work of the secretariat & working groups; (b) among network members mutually

## Slide 11: Network development (2/5)
Members have possibilities to participate in decision-making and activities => feeling of ownership of the network
  Challenges:
    Unbalanced participation of members: common in networks, but care should be taken not to become too much a ‘club of insiders’
    Underrepresentation of the South and GUFs
      Participation of the South: has increased, but still much to do
      Participation GUFs: demand for clarifying the relationship between GUFs and ITUC/TUDCN

## Slide 12: Network development (3/5)
Network structure:
  Secretariat:
    Highly appreciated by members; competent staff
    Risks: to work too autonomously; to focus too much on external work (v. internal network strengthening and member participation)
  FSG: not yet fully taking up its role as governance structure, despite attempts for improvement
  General meetings:
    important networking moment
    Overloaded agendas => little time for liaising, exchange and networking
  Working groups:
    Outputs highly valued by network members.
    Small number of active participants (especially Development Effectiveness WG)

## Slide 13: Network development (4/5)
Good communication and information sharing mechanisms in place
  TUDCN website, monthly newsletter, projects directory, position papers and briefing notes, …
  Highly appreciated: allow to remain informed on what is going on in the network and on evolutions in the global development agenda
  Especially the newsletter and ITUC briefing notes considered highly useful
  Weaknesses:
    Mailing list not up-to-date.
    Member participation in communication is low, mainly due to time constraints

## Slide 14: Network development (5/5)
Major constraint: weak institutionalisation within the ITUC + weak political support for the network
  TUDCN seen as a project, not as an intrinsic part of the work of the ITUC
  Poor understanding of: (1) development cooperation; (2) the role and added value of TUDCN
  Consequences:
    Legitimacy and sustainability of the network affected
    Missed opportunities (e.g. in terms of advocacy)
  Needed:
    Political recognition of TUDCN
    Political decision to support the further institutional development of TUDCN
    But: some degree of independency needed due to the network character of TUDCN

## Slide 15: Internal achievements (1/2)
Strengthened views on development cooperation and practices, among others via ‘TU principles and Guidelines’:
  better positioning within CSO community
  better articulating of own identity
TUs opening up for development cooperation issues to some degree, but all-in-all still rather shallow levels of inclusion and ownership of development cooperation in TUs

## Slide 16: Internal achievements (2/2)
Increased coordination and coherence of TU development cooperation
  Before TUDCN: much inefficiency, duplication, competition
  Creation of TUDCN filled in an important void
  Important challenges remain, in particular in the South: cooperation in Southern countries and South – South cooperation still weak
Increased TU capacity and effectiveness for development cooperation
  via ‘technical’ activities:
    TUDEP
    guidance note on M&E (in process)
  but here also, actual use within organisations remains a challenge

## Slide 17: External achievements (1/2)
Significant contribution to common TU positions with regard to development and development cooperation
  So far, relatively easy to develop such common positions
  Challenge for the future: representation issue - way of organising internal consultation (mainly Secretariat that takes initiative – no bottom-up approach to derive messages from members)
Increased visibility and recognition of TUs as development actors in their own right
  continuous and skilful involvement in key CSO platforms (Development Effectiveness debate, EU structured dialogue) as main trigger
  increased visibility and recognition at regional level: not clear
  here also future challenge related to representation

## Slide 18: External achievements (2/2)
Enhanced TU contributions in development debates and policies:
  closely linked to previous achievement (visibility and recognition)
  several success stories at national level (extent of changes at this level not clear)
This ‘must’ have led to ‘some influence’ on outcomes of development debates - typical TU preoccupations (decent work, ...) brought in. But:
  TUDCN acting rather reactively than proactively
  High quality inputs in debates seen by some as not sufficiently complemented by comprehensive campaigning strategy
Improved networking and cooperation
  TUs now occupying important position in many CSO platforms (with positive effect on representation and legitimacy of these platforms)

## Slide 19
III. Conclusions & Lessons learned

## Slide 20: Conclusions (1/2)
TUDCN succeeded to develop itself into a network that is fairly stable, inclusive, representative and legitimate
TUDCN clearly worked along its mandate of improving TU development effectiveness and ensuring input of TU views in development policy debates
Clear signs that TUDCN’s work in these areas has been effective to an important degree
TUDCN has the possibility to further develop the considerable potential of TU involvement in development cooperation and, more generally, in promoting a more equal, democratic and sustainable development

## Slide 21: Conclusions (2/2)
Challenges:
  Sustainability of the network: not yet guaranteed
    ‘Sustainability’ has not really been an issue in the network
    Main challenges:
      Dependence on external grants
      TUDCN’s unclear position under the ITUC umbrella
  High level of dependence on individuals
  Representation and legitimacy
    Might increasingly become under scrutiny by both external and internal partners

## Slide 22: Lessons learned
Effective network development:
  Is a complicated process
  Needs time, resources and strategic competence and direction
Combination between internal and external objectives is possible
  Synergic effects can be produced
  But: requires permanent balancing between both types of objectives
Key factor (so far) for success and recognition = the quality and consistency of contributions of network representatives (rather than the fact that they represent powerful mass organisations)

## Slide 23
IV. Recommendations

## Slide 24: Recommendations (1/4)
Continue + strategically expand + (in some cases) redirect existing efforts => to maintain the momentum gained and to safeguard the achievements of the past
Increase southern membership, incl.:
  Measures to make voice of the South more consistently heard
  Mechanisms to bring southern concerns and priorities more systematically on the advocacy agenda
Address representation and legitimacy more systematically:
  Increase southern participation
  Optimise internal consultation and representation mechanisms
  Explore possibilities to increase GUF participation

## Slide 25: Recommendations (2/4)
Sustain, via TUDCN, the TUs’ dynamic engagement and leadership role in the CSO forums and platforms:
  Continue to engage in issues that come up via international dynamics, but become somewhat more proactive here
  Engage more consistently in in-country level work (via members)
  Critical analysis and identification of the issues and forums TUDCN should concentrate on. Hereby:
    Broaden the institutional targets (aside from the EU and the post-Busan process)
    Focus on advocacy issues close to the core of TUDCN as a TU network
Give proportionally more attention to internal capacity building
  Incl.: support members to mainstream and/or diffuse tools & approaches in their organisations, partnerships and projects

## Slide 26: Recommendations (3/4)
Develop a comprehensive sustainability strategy, addressing:
  Organisational sustainability:
    Further consolidation of the network
    Particular attention to the present over-dependence on individuals
  Institutional sustainability: clarify position towards and within the ITUC
  Financial sustainability: develop a strategy to gradually become less dependent on external funding
Develop a campaigning approach and strategy, to make better use of the potential of the members in advocacy
Open the debate on the specific nature and interests of TUs within the broader CSO family

## Slide 27: Recommendations (4/4)
Further consolidate and develop the network internally:
  Optimise and diversify consultation and participation mechanisms
  Use General Meetings as a means to more actively engage members
  Strengthen the FSG
  Be a more formal in membership management
  Make mailing list up-to-date
  Continue to use short briefing papers to diffuse important messages
  Give more attention to internal capitalisation of experiences
  Discuss on how to further proceed with the work on M&E
Increase the resources of the network (incl.: expansion of the secretariat)

## Slide 28
South Research CVBA - VSO
Leuvensestraat 5/2
B - 3010 Kessel - Lo
Belgium
T +32 (0) 16 49 83 16
F +32 (0) 16 49 83 19
BE 0429 809 077
RPR Leuven
www.southresearch.be
info@southresearch.be